## Slide 1
WCC STRATEGIC PLANNING
EMP & Student Equity Plan

## Slide 2: Timeline
STEERING COMMITTEE COMMUNICATION
Invitation to the Steering Committee Kickoff on August 6, homework, and presentation of the planning process
July 2025
STEERING COMMITTEE KICKOFF
Facilitated engagement to:
a) agree on the outcome, roles, and timeline
b) receive guidance from President on vision formation
c) form the hindsight needed to move toward a future vision
d) draft a future vision inclusive of elements from the past and present to carry into the future
6 Aug 2025
STAKEHOLDER VISIONING WORKSHOP(S)
Two 1-hour facilitated workshops with approximately 30 invited stakeholders per workshop in a ‘max-mix’ arrangement to hear their aspirations for WCC
8 Aug 2025
CONSOLIDATION OF FUTURE VISION INPUT
Form a ‘North Star’ vision for the WCC strategic plan, and consider:
an aspiration summary statement that would inspire our campus and supporters
a metaphor and symbolism to describe the vision and outcomes of our effort
Aug 2025
STRATEGY AND GOAL FORMATION
Formation and articulation of our path forward inclusive of the bold steps needed, objectives, tactics, key performance indicators, and a roadmap for implementation
Vision and goal setting workshop with Student Equity Group and incorporates the Student Equity Plan content
Goal-setting workshop
Sept - Oct 2025
COMMUNICATION OF THE DRAFT PLAN FOR FEEDBACK
Invitation to the broader campus community to provide feedback on the draft strategic plan
Nov 2025 - end of Jan 2026
PLANNING DOCUMENT REFINEMENT
Finalization of the strategic plan content
Feb - Mar 2026
PUBLICATION PREPARATION
Prepare the strategic plan for public presentation inclusive of a roll-out strategy
Mar - Apr 2026
PRESENTATION OF THE 2026 - 2030 STRATEGIC PLAN
Spring 2026
Date TBD
IMPLEMENTATION UNDERWAY

## Slide 3
Align Student Equity Plan Metrics
Successful Enrollment
Persistence
Completion
Transfer to
4-Year
Transfer-level
Math & English

## Slide 4: Summary - August 6, 2025 Steering Committee Workshop